## RM Phase 2 - 14.06.22
Defect # | Title | Clarification | Severity | Priority
88901 | DIA ITE - WebPC not receiving response from DAON | Intermittent issue with Web Photo Capture communication with IVS. | 3 - Medium | 1
79003 | (TR) Token may be assigned to multiple users | In a unique edge case scenario it is possible for the same token to be registered to two accounts. | 3 - Medium | 2
80330 | IVS Technical Errors are displayed as Apply status on Dashboard | On Account, messaging displayed to user if IVS is down needs refinement | 3 - Medium | 2
84328 | DIA UAT: Assert to EC- Always share agency - User should be asked to reconsent when details have changed | Edge case affecting only DIA AML. If a user has had a name change after the initial eduring consent was given, they are not currently being prompted to provide a new consent next time their details are asserted | 3 - Medium | 2
85359 | DIA ITE: Experiencing slowness logging in to account | Login to the Account home page was initially taking longer than expected. Response times are now better, though being monitored | 3 - Medium | 2
86930 | DIA UAT: Assert to EC- Always share agency - when User reconsents when details have changed, expire and re-write EC record | Edge case scenario where user has changed name since original Enduring Consent was given two consents are showing. | 3 - Medium | 2
86059 | Safari Browser - 2FA page mapped to "Cancel" Button and auto-fill code bug | Existing production defect for Safari iPhone users. Default button on 2FA page is mapped to "Cancel" rather than "Confirm Code". | 3 - Medium | 2
87975 | DIA UAT: Audit Logs - 8021 is incorrectly recorded during additional flows | New audit event for first time identity assertions is being recorded incorrectly in some flows. | 3 - Medium | 2
88902 | DIA: Assertion activity event should not be written in IVS for returning user to Don't share agency | Assertion event being incorrectly written to IVS for "Don't Share" agencies | 3 - Medium | 2
88963 | DIA UAT: Audit Logs - 8022 is incorrectly recorded for user who cancels consent during asserting to Identity & Address to agency | New audit event for first time identity and address assertions is being recorded incorrectly in som eflows. | 3 - Medium | 2
89525 | DIA ITE: HD Activity Report slow to load/not loading intermittently | In the HD, the Activity list for accounts with a large number of audit events is slow to load or not loading intermittently. | 3 - Medium | 2
89559 | Assertion Service: Consent and audit logs are not being recorded when the agency is release consent and always share flag is false | Consent/audit logs for assertions against an agency which is set to not share details are not being logged | 3 - Medium | 2
88531 | DIA UAT: Remove token pop-up box format inconsistent | Minor formatting issue on remove token pop up | 3 - Medium | 3
89074 | DIA: User Consents - we should only show a max of 10 records per page | Number of consents shown per page on pagination is inconsistent. | 3 - Medium | 3